## Master list
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Grant Tracking spreadsheed updated through 3/31 | Debra / Paige / Camelia | 2024-05-01
Purchase order cutoff | FYI only | 2024-05-17
Interim Audit May 20th-22nd
Do OPEB contribution (if budgeted) | Kristin | 2024-05-17
Write offs for Housing accounts due to Housing Executive Assistant for council agenda | Camelia | 2024-05-24
Write offs for MB accounts due to Kristin for council approval | Carrie | 2024-05-30
Record Loan Pmt from Housing Capital Fund to GF | Camelia | 2024-06-07
Send HUD-52574 to CMO for Mayor's signature afer council approval | Camelia | 2024-06-14
Do JEs/BAs to close any funds/budget units as needed | Debra / Paige / Camelia | 2024-06-14
Verify IT will be available to assist w/ FYE procedures | Kristin | 2024-06-14
Import budget from Questica into Budget Prep module & fix errors | Kristin | 2024-06-14
Remove any closed funds/budget units and unused accounts from setup in both Budget Prep and Fund Accounting | Kristin | 2024-06-21
Write off in HAB bad debts approved by Council | Camelia | 2024-06-21
JE for Housing bad debts approved by Council | Camelia | 2024-06-21
Send reminder to airport about 6/30 inventory count | Steve | 2024-06-21
A/P deadline for all FY24 petty cash reimbursements | AP | 2024-06-25
Remind Communications, Data Services of inventory count needed by 12PM 6/30 | Carrie | 2024-06-25
Send email asking everyone to logout of FinPlus @ 4 on 6/30 | Kristin | 2024-06-26
Last payroll in FY24, P/E 6/23/24, post to period 12 FY24 | Bridgen | 2024-06-27
Make sure all monthly, quarterly reports are saved prior to FYE process | Bridgen | 2024-06-27
Physical inventory count at warehouse | Carrie | 2024-06-28
Last check run FY24. Will pay out all open payables for FY24. | AP | 2024-06-28
Run Accrued Vacation reports used for FYE JEs (Crystal report) | Madi | 2024-06-28
Payroll FYE processes | Bridgen | 2024-06-28
Count all cash drawers, petty cash and change funds | Madi | 2024-06-28
Run list of active Fire employees - pension count for note disclosure | Kristin | 2024-06-28
Change payroll deductions (retirement, 401k) for new FY | Bridgen | 2024-06-28
Reconcile WMS to Finance Plus (Inventory) | Carrie | 2024-06-28
Run final catalog reports to Excel for all BOC warehouses | Carrie | 2024-06-28
FYE Processes in Fin Plus for Warehouse module by 4PM | Carrie | 2024-06-28
Send signed HUD-52574 to HUD-Greensboro | Camelia | 2024-06-28
Run FYE process and post new year budget to Fund Accounting | Kristin | 2024-06-28
Verify all closed projects/funds do not roll forward with new budget. If they do, remove them from FY24 setup. | Kristin | 2024-06-28
Record Embassy Payment made in June for July as Deferred Revenue | Cindy | 2024-06-28
Generate and save leave balance report following last payroll (GASB101) | Madi | 2024-06-28
Identify June pCard transactions w/ July post date to prepare JE - contact depts for coding | Madi | 2024-07-05
Record Accrued Vacation | Madi | 2024-07-05
Regular monthly journal entries | All | 2024-07-10
Record retiree insurance paid as well as payments received from retirees to Fund 760 | Madi | 2024-07-10
Record Interest Payable and reversal in July | Kristin | 2024-07-10
Record accrual for p-card transactions from the July stmt w/ June transaction dates | Madi | 2024-07-12
First pay in FY24, P/E 7/7, post to period 1 FY25 | Bridgen | 2024-07-12
Reverse Prev FY market adjustment in FY24 | Kristin | 2024-07-12
Schedule showing vacation accrual | Madi | 2024-07-12
Run list of active CIP from Fixed Assets - email depts to ask for est completion date | Steve | 2024-07-12
Cutoff date for A/P invoices for FY24, will be paid 7/19 | AP | 2024-07-16
After 7/12 payroll, record accrued payroll and fringe benefits for 6/24-6/30 - also record reversal in July FY24 | Bridgen | 2024-07-17
Schedule showing payroll & benefits accrual by fund "Payroll accrual summary" | Bridgen | 2024-07-17
Request workers comp loss run report from Risk Mgmt | Kristin | 2024-07-17
BCBS IBNR reports - request from HR | Kristin | 2024-07-17
Lease review complete. Additions, modifications, terminations entered in Debtbook | Kristin | 2024-07-19
Subscription review complete. Additions, modifications, terminations entered in Debtbook | Kristin | 2024-07-19
Ensure all revenue for July P&R events are recorded as deferred revenue | Cindy | 2024-07-19
Last AP Check run for FY24 | FYI only | 2024-07-19
Email Stat Section info to departments - give due date of 8/16 | Carrie | 2024-07-19
Adjust inventory to physical count - fleet | Carrie | 2024-07-19
Adjust inventory to physical count - signals | Carrie | 2024-07-19
Record receivable for July Cycle 1 in FY24 | Rita | 2024-07-19
Record reversal for July Cycle 1 in FY25 | Rita | 2024-07-19
Do JE to record vehicle/property tax receivable from County | Rita | 2024-07-19
Do JE to record additonal lot cleaning revenue from County | Rita | 2024-07-19
General Operating Recon | Carrie | 2024-07-19
NCCMT-General Recon | Carrie | 2024-07-19
NCCMT-GO Bond Acct Recon | Carrie | 2024-07-19
Workers Comp Bank Recon | Carrie | 2024-07-19
Recon for Money Market account (990-1100144) | Carrie | 2024-07-19
Host Fees escrow recon (990-1100157) | Carrie | 2024-07-19
Recons for all misc billing accounts | Carrie | 2024-07-19
Misc Billing CC recon (1125152 & 1125153) | Carrie | 2024-07-19
Performance guarantee recon by fund (2213502) | Carrie | 2024-07-19
Suspense account recon | Carrie | 2024-07-19
Sidewalk escrow account recon | Carrie | 2024-07-19
Deferred revenue recon | Carrie | 2024-07-19
Sales tax payable recon | Carrie | 2024-07-19
Emergency response reimb recon | Carrie | 2024-07-19
Retainage payable schedule by fund | AP | 2024-07-19
Record accruals for bank drafts | Cindy | 2024-07-19
Record accruals for purchased power | Steve | 2024-07-19
Recon for all investments | Kristin | 2024-07-19
Send reminder email to Engineering about developer donated asset info needed - need info by 8/2 | Steve | 2024-07-19
Record Sales Tax receivable for amt received in July | Jessica | 2024-07-19
Record Franchise Tax receivable | Jessica | 2024-07-19
Record receivable for June Accela | Carrie | 2024-07-19
Adjust inventory to physical count - warehouse | Carrie | 2024-07-19
Record all adjustments/corrections from physical asset verification | Steve | 2024-07-19
Record all asset disposals | Steve | 2024-07-19
Record all asset transfers | Steve | 2024-07-19
Golf Course Bank Recon | Steve | 2024-07-19
Airport CC recon | Steve | 2024-07-19
Airport A/R aging recon | Steve | 2024-07-19
Golf Course A/R recon | Steve | 2024-07-19
Detail list of warehouse inventory items on hand at year end. | Carrie | 2024-07-19
Golf Course inventory listing | Steve | 2024-07-19
Airport fuel inventory listing | Steve | 2024-07-19
Fleet inventory listing | Carrie | 2024-07-19
Golf course rainchecks listing | Steve | 2024-07-19
Golf course gift certificates listing | Steve | 2024-07-19
Request from Amanda spreadsheet for final cost allocations due 8/9 | Steve | 2024-07-19
Allocate investment earnings based on cash balance (do not post before July 15th when most June cash entries should be done) | Kristin | 2024-07-19
Record investment interest receivable P13, reversal in July P1 | Kristin | 2024-07-19
Record investment market adjustment P13 | Kristin | 2024-07-19
Analysis of all installment financings | Kristin | 2024-07-19
Reconciliation of debt accrued interest expense to GL | Kristin | 2024-07-19
List of all open encumbrances as of June 30 | Kristin | 2024-07-22
Roll PO's to new FY | Kristin | 2024-07-22
Do interim close after PO roll | Kristin | 2024-07-22
Do JE to record retainage payable in FY24 and reversal in FY25 | Madi | 2024-07-22
Do one sided budget amendment to put system back in balance after PO rollforward | Kristin | 2024-07-22
Interest receivable recon | Kristin | 2024-07-22
Send report to purchasing after PO's roll for any adjustments that need to be made to PO balance in new FY | AP | 2024-07-23
June P-Card transactions posting | FYI only | 2024-07-23
Record accrual for June p-card stmt | AP | 2024-07-23
Record accrual reversal/payment for June p-card stmt in FY24 | AP | 2024-07-24
Powell Bill asset information to Paige | Steve | 2024-07-24
Allocate Powell Bill through period 13 | Paige | 2024-07-24
Prepaid expense recon | AP | 2024-07-24
Recon for investments after int allocation, int receivable, market adjustment | Kristin | 2024-07-26
Record reversal of all deferred revenue from FY24 in FY25 revenue accts | Cindy | 2024-07-26
Record receivable for July Cycle 2 in FY24 | Rita | 2024-07-26
Record reversal for July Cycle 2 in FY25 | Rita | 2024-07-26
Adjust Reserved FB - Mayors tournament | Cindy | 2024-07-26
Adjust Reserved FB - Youth Council | Cindy | 2024-07-26
Adjust Reserved FB - Clearwater | Cindy | 2024-07-26
Adjust Reserved FB - Elec Mgmt Funds | Cindy | 2024-07-26
Adjust Reserved FB - RICO | Debra | 2024-07-26
Adjust Reserved FB - 66 Union | Cindy | 2024-07-26
Recon for all investments after allocation/market adj/interest accrual | Kristin | 2024-07-26
Recon for all trustee accts (restricted cash) | Kristin | 2024-07-26
Renewal stmt for ext & repl CD | Kristin | 2024-07-26
Stmts for any other CDs/funds recorded in 990-1100151 | Kristin | 2024-07-26
Copy of Wells Fargo investment statement | Kristin | 2024-07-26
Copy of OPEB stmt | Kristin | 2024-07-26
Recons for Airport deposit accounts | Steve | 2024-07-26
Airport Fuel Revenue/Expense spreadsheets | Steve | 2024-07-26
Purchase power spreadsheet | Steve | 2024-07-26
Reconciliation of City's retirement system contributions | Bridgen | 2024-07-26
Reconciliation of 401k contributions | Bridgen | 2024-07-26
Letter from retirement system about contribution rates eff 7/1/24 | Bridgen | 2024-07-26
941/Payroll Expense reconciliation | Bridgen | 2024-07-26
Do JE to reverse prepaid expense in FY25 (after POs roll) | AP | 2024-07-26
Record all governmental vehicle & equipment additions | Steve | 2024-07-26
Copy of LGC 203 Report | Kristin | 2024-07-26
Utilities revenue spreadsheet | Steve | 2024-07-26
Water/Sewer & Electric Consumption Reports | Steve | 2024-07-26
Top Water/Sewer/Electric Customers | Steve | 2024-07-26
Adjust utility deposit accounts to agree to Harris | Rita | 2024-07-26
Adjust utility receivable accounts to agree to Harris | Rita | 2024-07-26
Record bad debt expense and writeoffs and allowance adj | Carrie / Rita | 2024-07-26
Accounts payable recon by fund | AP | 2024-07-26
Reconcile Electric Sales tax spreadsheet to GL after cycle 2 posted | Steve | 2024-07-26
Work with Electric to get info on projects recorded in operations to determine if any are capital | Steve | 2024-07-26
Review housing 1001 assets to determine proper adjustments | Steve | 2024-07-26
Budget amendment to adjust CDBG PI, salary/benefits to actual for FY24 | Paige | 2024-07-26
Budget amendment to adjust HOME PI, salary/benefits to actual for FY24 | Paige | 2024-07-26
Adjust Reserved FB - Powell Bill | Paige | 2024-07-26
Backup for Ricoh Reserved FB | Debra | 2024-07-26
Backup for reserved fund balance amounts | Cindy | 2024-07-26
Subscription payments recorded in Debtbook | Kristin | 2024-07-26
Lease payments recorded in Debtbook | Kristin | 2024-07-26
Run balance sheet, expenditure status, revenue status before posting rest of JEs
Record all enterprise fund vehicle & equipment additions | Steve | 2024-07-31
Record all computer/software/building/land additions | Steve | 2024-07-31
Record all other additions from 55 accounts not yet posted | Steve | 2024-07-31
Do interim close | Kristin | 2024-07-31
Printout from Harris showing A/R aging | Rita | 2024-07-26
Backup for receivable from Cab County for MV tax | Rita | 2024-07-26
Backup for receivable from Cab County for Accela | Carrie | 2024-07-26
Copies of Utility accrual calculation | Rita | 2024-07-26
Utility A/R aging recon | Rita | 2024-07-26
Utility CC recon | Rita | 2024-07-26
Allowance for Doubtful accts recon | Rita | 2024-07-26
Utility Deposit recon | Rita | 2024-07-26
Reduce Installment loans for principal pmts | Kristin | 2024-07-26
Record new debt and reduce proceeds | Jessica | 2024-07-26
Record amortization of bond discount, bond premium, and refunding loss | Jessica | 2024-07-26
Record Pension liability | Kristin | 2024-07-26
Record Health IBNR Claims | Kristin | 2024-07-26
Record WC reserve liability | Kristin | 2024-07-26
Reduce Debt for Principal Pmts | Kristin | 2024-07-26
Record housing asset adjustments/cleanup | Steve | 2024-07-31
Record electric operations project additions | Steve | 2024-07-31
Record additions for all 58 accounts Compare with completion date provided by dept to ensure all captured. If dept says complete, there should be no open PO on project account. | Steve | 2024-07-31
Record water/sewer contributed capital | Steve | 2024-08-01
Record street contibuted capital (new JE) | Steve | 2024-08-01
After all additions are entered in fixed asset module, review active CIP to see if any need to be put into service (based on est completion date or PO status) | Steve | 2024-08-01
Generate, review and submit lease JE from Debtbook | Kristin | 2024-08-02
Generate, review and submit subscription JE from Debtbook | Kristin | 2024-08-02
After all additions are entered, review capital outlay accts to ensure none are missing before posting depreciation | Steve | 2024-08-02
Housing Bank Acct Recon (final version with all items corrected) | Carrie | 2024-08-02
Depository Recon (final version with all items corrected) | Carrie | 2024-08-02
Record Police separation allowance to Fund 950 | Madi | 2024-08-02
Housing FYE entries (A/R aging, accruals, Record A/R for negative RNP) | Camelia | 2024-08-02
Do JE to adjust ad valorem (general fund) receivable to actual | Rita | 2024-08-02
Do JE to adjust Municipal Serv District tax receivable to actual | Rita | 2024-08-02
Record receivables for grants at year end | Paige / Camelia / Debra | 2024-08-02
Public Housing AR/Repay Recon (690-1211050/1125000) | Camelia | 2024-08-02
Portability AR Recon (210-1211250) | Kristin | 2024-08-02
Market Rate AR Recon (350-1211050) | Camelia | 2024-08-02
Tenant security deposits recon (690-2213523) | Camelia | 2024-08-02
Market Rate security deposit recon (350-2213523) | Camelia | 2024-08-02
Fund 690 Escrow recon (690-2351000) | Camelia | 2024-08-02
Fund 210 Escrow recon (210-2351000) | Camelia | 2024-08-02
Copy of Police Separation Allowance Actuarial Valuation | Madi | 2024-08-02
Tax receivable schedules | Rita | 2024-08-02
Tax levy schedule for ACFR | Rita | 2024-08-02
Deferred or prepaid property taxes | Rita | 2024-08-02
A/R report from County for all property tax years | Rita | 2024-08-02
Initial Tax Scroll Summary | Rita | 2024-08-02
Electronic copy of tax scroll | Rita | 2024-08-02
Powell Bill Expenditure Report w/ backup (copy for auditor) | Paige | 2024-08-02
Listing of City Streets paved or resurfaced for Powell Bill (copy for auditor) | Paige | 2024-08-02
Copy of Certified Statement for Powell Bill (copy for auditor) | Paige | 2024-08-02
List of all Powell Bill contracts awarded in FY including amounts | Paige | 2024-08-02
Debt spreadsheet | Kristin | 2024-08-02
Record any CIP put into service | Steve | 2024-08-02
Recon for all grant related receivables | Paige / Camelia / Debra | 2024-08-05
Final Grant Tracking spreadsheet updated through 6/30 | Paige / Camelia / Debra | 2024-08-06
Record depreciation (save reports in Excel for auditors) | Steve | 2024-08-06
Adjust contributed capital balances after depreciation is posted | Steve | 2024-08-07
Allocation of internal service fund | Steve | 2024-08-08
Generate lease audit notes from Debtbook and compare rollforwards to GL | Kristin | 2024-08-09
Generate subscription audit notes from Debtbook and compare rollforwards to GL | Kristin | 2024-08-09
JE to transfer from GF to Housing based on actual cost allocation up to budgeted amount | Camelia | 2024-08-09
JE to transfer from GF to Vouchers based on actual cost allocation up to budgeted amount | Camelia | 2024-08-09
Reconciled fixed asset spreadsheet for each fund | Steve | 2024-08-09
Equity rollforward | Kristin | 2024-08-09
Copy of detail listing of additions, retirements and other adjustments for the year (Excel sheet for additions should include recon back to GL expense accounts for auditors) | Steve | 2024-08-09
Provide a copy of the detail depreciation listing | Steve | 2024-08-09
List of all contributed capital assets | Steve | 2024-08-09
List of all infrastructure assets capitalized during the year and their related supporting documentation | Steve | 2024-08-09
List of active CIP as of FY with estimated completion dates | Steve | 2024-08-09
Audit trail (Excel) for all 4351000 accounts | Steve | 2024-08-09
Transfer recon | Carrie | 2024-08-09
Due to/from recon | Carrie | 2024-08-09
Fund 990 Due to/from recon | Carrie | 2024-08-09
Copy of OPEB Actuarial Valuation | Madi | 2024-08-08
Record OPEB liability per actuarial valuation | Kristin | 2024-08-09
Record solid waste disposal tax receivable (received in August) | Cindy | 2024-08-12
Move add'l expenses for disposal tax once receivable is recorded | Cindy | 2024-08-12
Record Sales Tax receivable for amt received in August and estimate for amt to be received in September | Jessica | 2024-08-12
Update Docuware and Works to reflect active, budgeted GL accounts | Madi | 2024-08-16
Do interim close | Kristin | 2024-08-16
Send Risk Management note disclosure to Risk to update - due 9/8 | Kristin | 2024-08-23
Submit unaudited FDS to HUD | Camelia | 2024-08-30
FDS Schedule for ACFR | Camelia | 2024-08-30
Final Audit August 26th - 30th
Fixed asset reports for ACFR (ensure all rollforwards balance to prev FY) | Steve | 2024-08-30
Investment note disclosure updated | Kristin | 2024-09-04
Statistical section completed | Carrie | 2024-09-06
Have budget cover modified for ACFR | Kristin | 2024-09-06
Do interim close | Kristin | 2024-09-06
Record reversal for June pcard trxns on July stmt (paid in Aug) | Madi | 2024-09-10
Have draft of ACFR to auditors for them to review | Kristin | 2024-09-30
ACFR due to LGC | Kristin | 2024-10-31
AFIR due to LGC | Kristin | 2024-10-31
Adjust Restricted by State Statute (after ACFR draft is done) | Kristin | 2024-10-31
File Data Collection Form | Kristin | 2024-10-31
Send copy of final ACFR to WSACC (wheglar@wsacc.org) | Kristin | 2024-11-15
Get draft of audit presentation from auditors | Kristin | 2024-11-22
Rate covenants due to US Bank | Kristin | 2024-11-27
Add agenda item for audit presentation to Council | Kristin | 2024-12-02
Audit presentation to council (worksession) | Kristin | 2024-12-10
Do final close after LGC approved ACFR | Kristin | 2024-12-13
Application for Certificate Program to GFOA (due 12/30) | Kristin | 2024-12-20

## AP
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Purchase order cutoff | FYI only | 2024-05-17
A/P deadline for all FY24 petty cash reimbursements | AP | 2024-06-25
Last check run FY24. Will pay out all open payables for FY24. | AP | 2024-06-28
Regular monthly journal entries | All | 2024-07-10
Cutoff date for A/P invoices for FY24, will be paid 7/19 | AP | 2024-07-16
Last AP Check run for FY24 | FYI only | 2024-07-19
Retainage payable schedule by fund | AP | 2024-07-19
Send report to purchasing after PO's roll for any adjustments that need to be made to PO balance in new FY | AP | 2024-07-23
June P-Card transactions posting | FYI only | 2024-07-23
Record accrual for June p-card stmt | AP | 2024-07-23
Record accrual reversal/payment for June p-card stmt in FY24 | AP | 2024-07-24
Prepaid expense recon | AP | 2024-07-24
Do JE to reverse prepaid expense in FY25 (after POs roll) | AP | 2024-07-26
Accounts payable recon by fund | AP | 2024-07-26

## Bridgen
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Purchase order cutoff | FYI only | 2024-05-17
Last payroll in FY24, P/E 6/23/24, post to period 12 FY24 | Bridgen | 2024-06-27 | X
Make sure all monthly, quarterly reports are saved prior to FYE process | Bridgen | 2024-06-27 | x
Payroll FYE processes | Bridgen | 2024-06-28 | x
Change payroll deductions (retirement, 401k) for new FY | Bridgen | 2024-06-28 | x
Regular monthly journal entries | All | 2024-07-10
First pay in FY24, P/E 7/7, post to period 1 FY25 | Bridgen | 2024-07-12
After 7/12 payroll, record accrued payroll and fringe benefits for 6/24-6/30 - also record reversal in July FY24 | Bridgen | 2024-07-17 | x
Schedule showing payroll & benefits accrual by fund "Payroll accrual summary" | Bridgen | 2024-07-17
Last AP Check run for FY24 | FYI only | 2024-07-19
June P-Card transactions posting | FYI only | 2024-07-23
Reconciliation of City's retirement system contributions | Bridgen | 2024-07-26
Reconciliation of 401k contributions | Bridgen | 2024-07-26
Letter from retirement system about contribution rates eff 7/1/24 | Bridgen | 2024-07-26
941/Payroll Expense reconciliation | Bridgen | 2024-07-26

## Camelia
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Grant Tracking spreadsheed updated through 3/31 | Debra / Paige / Camelia | 2024-05-01
Purchase order cutoff | FYI only | 2024-05-17
Write offs for Housing accounts due to Housing Executive Assistant for council agenda | Camelia | 2024-05-24
Record Loan Pmt from Housing Capital Fund to GF | Camelia | 2024-06-07
Send HUD-52574 to CMO for Mayor's signature afer council approval | Camelia | 2024-06-14
Do JEs/BAs to close any funds/budget units as needed | Paige / Camelia / Debra | 2024-06-14
Write off in HAB bad debts approved by Council | Camelia | 2024-06-21
JE for Housing bad debts approved by Council | Camelia | 2024-06-21
Send signed HUD-52574 to HUD-Greensboro | Camelia | 2024-06-28
Regular monthly journal entries | All | 2024-07-10
Last AP Check run for FY24 | FYI only | 2024-07-19
June P-Card transactions posting | FYI only | 2024-07-23
Housing FYE entries (A/R aging, accruals, Record A/R for negative RNP) | Camelia | 2024-08-02
Record receivables for grants at year end | Paige / Camelia / Debra | 2024-08-02
Public Housing AR/Repay Recon (690-1211050/1125000) | Camelia | 2024-08-02
Market Rate AR Recon (350-1211050) | Camelia | 2024-08-02
Tenant security deposits recon (690-2213523) | Camelia | 2024-08-02
Market Rate security deposit recon (350-2213523) | Camelia | 2024-08-02
Fund 690 Escrow recon (690-2351000 against June balance from HAB) | Camelia | 2024-08-02
Fund 210 Escrow recon (210-2351000 against June balance from HAB) | Camelia | 2024-08-02
Recon for all grant related receivables | Paige / Camelia / Debra | 2024-08-05
JE to transfer from GF to Housing based on actual cost allocation up to budgeted amount (after cost allocations posted) | Camelia | 2024-08-09 |  | Once Steve is done with Cost Allocations
JE to transfer from GF to Vouchers based on actual cost allocation up to budgeted amount (after cost allocations posted) | Camelia | 2024-08-09 |  | Once Steve is done with Cost Allocations
Final Grant Tracking spreadsheet updated through 6/30 | Paige / Camelia / Debra | 2024-08-12
Submit unaudited FDS to HUD | Camelia | 2024-08-30
FDS Schedule for ACFR | Camelia | 2024-08-30
Note on A29: Kristin: to account for Housing transfer from GF

## Carrie
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Purchase order cutoff | FYI only | 2024-05-17
Write offs for MB accounts due to Kristin for council approval | Carrie | 2024-05-30
Remind Communications, Data Services of inventory count needed by 12PM 6/30 | Carrie | 2024-06-25
Physical inventory count at warehouse | Carrie | 2024-06-28
Reconcile WMS to Finance Plus (Inventory) | Carrie | 2024-06-28
Run final catalog reports to Excel for all BOC warehouses | Carrie | 2024-06-28
FYE Processes in Fin Plus for Warehouse module by 4PM | Carrie | 2024-06-28
Regular monthly journal entries | All | 2024-07-10
Last AP Check run for FY24 | FYI only | 2024-07-19
Email Stat Section info to departments - give due date of 8/16 | Carrie | 2024-07-19
Adjust inventory to physical count - fleet | Carrie | 2024-07-19
Adjust inventory to physical count - signals | Carrie | 2024-07-19
General Operating Recon | Carrie | 2024-07-19
NCCMT-General Recon | Carrie | 2024-07-19
NCCMT-FSS Trust Recon | Carrie | 2024-07-19
NCCMT Public Housing Trust recon | Carrie | 2024-07-19
Utility Lockbox Acct Recon | Carrie | 2024-07-19
Workers Comp Bank Recon | Carrie | 2024-07-19
Recon for Money Market account (990-1100144) | Carrie | 2024-07-19
Host Fees escrow recon (990-1100157) | Carrie | 2024-07-19
Recons for all misc billing accounts | Carrie | 2024-07-19
Misc Billing CC recon (1125152 & 1125153) | Carrie | 2024-07-19
Performance guarantee recon by fund (2213502) | Carrie | 2024-07-19
Suspense account recon | Carrie | 2024-07-19
Sidewalk escrow account recon | Carrie | 2024-07-19
Deferred revenue recon | Carrie | 2024-07-19
Sales tax payable recon | Carrie | 2024-07-19
Cell Tower revenue recon (100/620-4341660) | Carrie | 2024-07-19
Emergency response reimb recon | Carrie | 2024-07-19
Record receivable for June Accela | Carrie | 2024-07-19
Adjust inventory to physical count - warehouse | Carrie | 2024-07-19
Detail list of warehouse inventory items on hand at year end. | Carrie | 2024-07-19
Fleet inventory listing | Carrie | 2024-07-19
June P-Card transactions posting | FYI only | 2024-07-23
Record bad debt expense and writeoffs and allowance adj | Carrie / Rita | 2024-07-26
Backup for receivable from Cab County for Accela | Carrie | 2024-07-26
Housing Bank Acct Recon (final version with all items corrected) | Carrie | 2024-08-02
Depository Recon (final version with all items corrected) | Carrie | 2024-08-02
Transfer recon | Carrie | 2024-08-09
Due to/from recon | Carrie | 2024-08-09
Fund 990 Due to/from recon | Carrie | 2024-08-09
Statistical section completed | Carrie | 2024-09-06

## Cindy
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Purchase order cutoff | FYI only | 2024-05-17
Record Embassy Payment made in June for July as Deferred Revenue | Cindy | 2024-06-28 | 2024-06-24
Regular monthly journal entries | All | 2024-07-10 | 2024-07-10
Ensure all revenue for July P&R events are recorded as deferred revenue | Cindy | 2024-07-19 | 2024-06-26
Last AP Check run for FY24 | FYI only | 2024-07-19
Record accruals for bank drafts | Cindy | 2024-07-19 | 2024-07-19
Move accrued bank drafts to correct cash fund | Cindy | 2024-07-31 | 2024-07-30
June P-Card transactions posting | FYI only | 2024-07-23
Record reversal of all deferred revenue from FY24 in FY25 revenue accts | Cindy | 2024-07-26 | 2024-07-02
Adjust Reserved FB - Mayors tournament | Cindy | 2024-07-26 | 2024-07-24
Adjust Reserved FB - Youth Council | Cindy | 2024-07-26 | 2024-07-24
Adjust Reserved FB - Clearwater | Cindy | 2024-07-26 | 2024-07-24
Adjust Reserved FB - Elec Mgmt Funds | Cindy | 2024-07-26 | 2024-07-24
Adjust Reserved FB - 66 Union | Cindy | 2024-07-26 | 2024-07-24
Backup for reserved fund balance amounts | Cindy | 2024-07-26 | 2024-07-24
Record solid waste disposal tax receivable (received in August) | Cindy | 2024-08-12 | 2024-08-20
Move add'l expenses for disposal tax once receivable is recorded | Cindy | 2024-08-12

## Debra
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Grant Tracking spreadsheed updated through 3/31 | Debra / Paige / Camelia | 2024-05-01 | 2024-05-01
Purchase order cutoff | FYI only | 2024-05-17 | 2024-05-17
Do JEs/BAs to close any funds/budget units as needed | Debra / Paige / Camelia | 2024-06-14 | 2024-06-14
Regular monthly journal entries | All | 2024-07-10 | 2024-07-10
Last AP Check run for FY24 | FYI only | 2024-07-19 | 2024-07-19
June P-Card transactions posting | FYI only | 2024-07-23
Adjust Reserved FB - RICO | Debra | 2024-07-26 | 2024-07-25
Backup for Ricoh Reserved FB | Debra | 2024-07-26 | 2024-07-25
Record receivables for grants at year end | Paige / Camelia / Debra | 2024-08-02 | 2024-08-01
Recon for all grant related receivables | Paige / Camelia / Debra | 2024-08-05 | 2024-08-07
Final Grant Tracking spreadsheet updated through 6/30 | Paige / Camelia / Debra | 2024-08-06 | 2024-08-07
Note on D15: Debra Navey: Retainage Posted 8.07.24 for Hangar TaxiLane
Note on D16: Debra Navey: Retainage Posted 8.07.24 for Hangar TaxiLane

## Jessica
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Purchase order cutoff | FYI only | 2024-05-17
Regular monthly journal entries | All | 2024-07-10 | 2024-07-09
Last AP Check run for FY24 | FYI only | 2024-07-19
Record Sales Tax receivable for amt received in July | Jessica | 2024-07-19 | 2024-07-09
Record Franchise Tax receivable | Jessica | 2024-07-19 | 2024-07-18
June P-Card transactions posting | FYI only | 2024-07-23
Record new debt and reduce proceeds | Jessica | 2024-07-26 | 2024-07-25
Record amortization of bond discount, bond premium, and refunding loss | Jessica | 2024-07-26 | 2024-08-05
Record Sales Tax receivable for amt received in August and estimate for amt to be received in September | Jessica | 2024-08-12 | 2024-08-09

## Kristin
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Purchase order cutoff | FYI only | 2024-05-17 | done
Do OPEB contribution (if budgeted) | Kristin | 2024-05-17 | 2024-05-23
Verify IT will be available to assist w/ FYE procedures | Kristin | 2024-06-14 | 2024-06-17
Import budget from Questica into Budget Prep module & fix errors | Kristin | 2024-06-14 | 2024-06-24
Remove any closed funds/budget units and unused accounts from setup in both Budget Prep and Fund Accounting | Kristin | 2024-06-21 | 2024-06-24
Send email asking everyone to logout of FinPlus @ 4 on 6/30 | Kristin | 2024-06-26 | 2024-06-27
Run list of active Fire employees - pension count for note disclosure | Kristin | 2024-06-28 | 2024-06-28
Run FYE process and post new year budget to Fund Accounting | Kristin | 2024-06-28 | 2024-06-28
Verify all closed projects/funds do not roll forward with new budget. If they do, remove them from FY24 setup. | Kristin | 2024-06-28 | 2024-07-16
Regular monthly journal entries | All | 2024-07-10 | 2024-07-10
Record Interest Payable and reversal in July | Kristin | 2024-07-10 | 2024-07-10
Reverse Prev FY market adjustment in FY24 | Kristin | 2024-07-12 | 2024-07-10
Request workers comp loss run report from Risk Mgmt | Kristin | 2024-07-17 | 2024-07-17
BCBS IBNR reports - request from HR | Kristin | 2024-07-17 | 2024-07-17
Allocate investment earnings based on cash balance (do not post before July 15th when most June cash entries should be done) | Kristin | 2024-07-19 | 2024-07-18
Lease review complete. Additions, modifications, terminations entered in Debtbook | Kristin | 2024-07-19 | 2024-08-06
Subscription review complete. Additions, modifications, terminations entered in Debtbook | Kristin | 2024-07-19 | 2024-08-09
Last AP Check run for FY24 | FYI only | 2024-07-19 | 2024-07-18
Recon for all investments | Kristin | 2024-07-19 | 2024-07-19
Record investment interest receivable P13, reversal in July P1 | Kristin | 2024-07-19 | 2024-07-19
Record investment market adjustment P13 | Kristin | 2024-07-19 | 2024-07-19
Analysis of all installment financings | Kristin | 2024-07-19 | None
Reconciliation of debt accrued interest expense to GL | Kristin | 2024-07-19 | 2024-08-06
List of all open encumbrances as of June 30 | Kristin | 2024-07-22 | 2024-07-21
Roll PO's to new FY | Kristin | 2024-07-22 | 2024-07-22
Do interim close after PO roll | Kristin | 2024-07-22 | 2024-07-22
Do one sided budget amendment to put system back in balance after PO rollforward | Kristin | 2024-07-22 | 2024-07-23
Interest receivable recon | Kristin | 2024-07-22 | 2024-07-31
June P-Card transactions posting | FYI only | 2024-07-23 | done
Recon for all investments after allocation/market adj/interest accrual | Kristin | 2024-07-26 | 2024-07-24
Recon for all trustee accts (restricted cash) | Kristin | 2024-07-26 | 2024-07-23
Renewal stmt for ext & repl CD | Kristin | 2024-07-26 | 2024-07-23
Stmts for any other CDs/funds recorded in 990-1100151 | Kristin | 2024-07-26 | N/A
Copy of Wells Fargo investment statement | Kristin | 2024-07-26 | 2024-07-23
Copy of OPEB stmt | Kristin | 2024-07-26 | 2024-07-23
Copy of LGC 203 Report | Kristin | 2024-07-26 | 2024-07-23
Subscription payments recorded in Debtbook | Kristin | 2024-08-02 | 2024-08-09
Lease payments recorded in Debtbook | Kristin | 2024-08-02 | 2024-08-06
Reduce Installment loans for principal pmts | Kristin | 2024-07-31 | 2024-08-01
Record Pension liability | Kristin | 2024-07-31 | 2024-08-22
Record Health IBNR Claims | Kristin | 2024-07-31 | 2024-08-02
Record WC reserve liability | Kristin | 2024-07-31 | 2024-08-02
Reduce Debt for Principal Pmts | Kristin | 2024-07-31 | 2024-08-01
Do interim close | Kristin | 2024-07-31 | 2024-08-03
Generate, review and submit lease JE from Debtbook | Kristin | 2024-08-02 | 2024-08-07
Generate, review and submit subscription JE from Debtbook | Kristin | 2024-08-02 | 2024-08-12
Portability AR Recon (210-1211250) | Kristin | 2024-08-02 | 2024-08-02
Debt spreadsheet | Kristin | 2024-08-02 | 2024-08-05
Generate lease audit notes from Debtbook and compare rollforwards to GL | Kristin | 2024-08-09 | 2024-08-07
Generate subscription audit notes from Debtbook and compare rollforwards to GL | Kristin | 2024-08-09 | 2024-08-14
Equity rollforward | Kristin | 2024-08-09 | 2024-08-16
Record OPEB liability per actuarial valuation | Kristin | 2024-08-09 | 2024-09-19
Do interim close | Kristin | 2024-08-16 | 2024-08-16
Send Risk Management note disclosure to Risk to update - due 9/8 | Kristin | 2024-08-23 | 2024-09-23
Investment note disclosure updated | Kristin | 2024-09-04 | 2024-09-06
Have budget cover modified for ACFR | Kristin | 2024-09-06 | 2024-09-24
Do interim close | Kristin | 2024-09-06 | 2024-09-09
Have draft of ACFR to auditors for them to review | Kristin | 2024-09-30
ACFR due to LGC | Kristin | 2024-10-31
AFIR due to LGC | Kristin | 2024-10-31
Adjust Restricted by State Statute (after ACFR draft is done) | Kristin | 2024-10-31
File Data Collection Form | Kristin | 2024-10-31
Send copy of final ACFR to WSACC (wheglar@wsacc.org) | Kristin | 2024-11-15
Get draft of audit presentation from auditors | Kristin | 2024-11-22
Rate covenants due to US Bank | Kristin | 2024-11-27
Add agenda item for audit presentation to Council | Kristin | 2024-12-02
Audit presentation to council (worksession) | Kristin | 2024-12-10
Do final close after LGC approved ACFR | Kristin | 2024-12-13
Application for Certificate Program to GFOA (due 12/30) | Kristin | 2024-12-20

## Madi
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Purchase order cutoff | FYI only | 2024-05-17
Run Accrued Vacation reports used for FYE JEs (Crystal report) | Madi | 2024-06-28 | x
Count all cash drawers, petty cash and change funds | Madi | 2024-06-28 | x
Generate and save leave balance report (all types) following last payroll (GASB101) | Madi | 2024-06-28 | x
Identify June pCard transactions w/ July post date to prepare JE - contact depts for coding | Madi | 2024-07-05 | x
Record Accrued Vacation | Madi | 2024-07-05 | x
Regular monthly journal entries | All | 2024-07-10 | X
Record retiree insurance paid as well as payments received from retirees to Fund 760 | Madi | 2024-07-10 | X
Record accrual for p-card transactions from the July stmt w/ June transaction dates | Madi | 2024-07-12 | X
Schedule showing vacation accrual | Madi | 2024-07-12
Last AP Check run for FY24 | FYI only | 2024-07-19
Do JE to record retainage payable in FY24 and reversal in FY25 | Madi | 2024-07-22
June P-Card transactions posting | FYI only | 2024-07-23
Record Police separation allowance to Fund 950 | Madi | 2024-08-02
Copy of Police Separation Allowance Actuarial Valuation | Madi | 2024-08-02
Copy of OPEB Actuarial Valuation | Madi | 2024-08-08
Update Docuware and Works to reflect active, budgeted GL accounts | Madi | 2024-08-16
Record reversal for June pcard trxns on July stmt (paid in Aug) | Madi | 2024-09-10 | prepared

## Paige
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Grant Tracking spreadsheed updated through 3/31 | Debra / Paige / Camelia | 2024-05-01 | 2024-04-30
Purchase order cutoff | FYI only | 2024-05-17
Do JEs/BAs to close any funds/budget units as needed | Debra / Paige / Camelia | 2024-06-14
Regular monthly journal entries | All | 2024-07-10
Last AP Check run for FY24 | FYI only | 2024-07-19
June P-Card transactions posting | FYI only | 2024-07-23
Allocate Powell Bill through period 13 | Paige | 2024-07-24 | 2024-07-23
Budget amendment to adjust CDBG PI, salary/benefits to actual for FY24 | Paige | 2024-07-26 |  | *Steve to complete
Budget amendment to adjust HOME PI, salary/benefits to actual for FY24 | Paige | 2024-07-26 |  | *Steve to complete
Adjust Reserved FB - Powell Bill | Paige | 2024-07-26 | 2024-07-24
Record receivables for grants at year end | Paige / Camelia / Debra | 2024-08-02 | 2024-08-01
Powell Bill Expenditure Report w/ backup (copy for auditor) | Paige | 2024-08-02 | 2024-07-25
Listing of City Streets paved or resurfaced for Powell Bill (copy for auditor) | Paige | 2024-08-02 | 2024-07-22 | *Request report from Devin Huston if you don't have a copy by 7/22
Copy of Certified Statement for Powell Bill (copy for auditor) | Paige | 2024-08-02 | 2024-07-22 | *Request report from Devin Huston if you don't have a copy by 7/23
List of all Powell Bill contracts awarded in FY including amounts | Paige | 2024-08-02 | 2024-07-31 | *Requested from Jillian on 7/24
Recon for all grant related receivables | Paige / Camelia / Debra | 2024-08-05 | 2024-08-05
Final Grant Tracking spreadsheet updated through 6/30 | Paige / Camelia / Debra | 2024-08-06 | 2024-08-21

## Rita
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Purchase order cutoff | FYI only | 2024-05-17
Regular monthly journal entries | All | 2024-07-10
Last AP Check run for FY24 | FYI only | 2024-07-19
Record receivable for July Cycle 1 in FY24 | Rita | 2024-07-19
Record reversal for July Cycle 1 in FY25 | Rita | 2024-07-19
Do JE to record vehicle/property tax receivable from County | Rita | 2024-07-19
Do JE to record additonal lot cleaning revenue from County | Rita | 2024-07-19
June P-Card transactions posting | FYI only | 2024-07-23
Record receivable for July Cycle 2 in FY24 | Rita | 2024-07-26
Record reversal for July Cycle 2 in FY25 | Rita | 2024-07-26
Adjust utility deposit accounts to agree to Harris | Rita | 2024-07-26
Adjust utility receivable accounts to agree to Harris | Rita | 2024-07-26
Record bad debt expense and writeoffs and allowance adj | Carrie / Rita | 2024-07-26
Printout from Harris showing A/R aging | Rita | 2024-07-26
Backup for receivable from Cab County for MV tax | Rita | 2024-07-26
Copies of Utility accrual calculation | Rita | 2024-07-26
Utility A/R aging recon | Rita | 2024-07-26
Utility CC recon | Rita | 2024-07-26
Allowance for Doubtful accts recon | Rita | 2024-07-26
Utility Deposit recon | Rita | 2024-07-26
Do JE to adjust ad valorem (general fund) receivable to actual | Rita | 2024-08-02
Do JE to adjust Municipal Serv District tax receivable to actual | Rita | 2024-08-02
Tax receivable schedules | Rita | 2024-08-02
Tax levy schedule for ACFR | Rita | 2024-08-02
Deferred or prepaid property taxes | Rita | 2024-08-02
A/R report from County for all property tax years | Rita | 2024-08-02
Initial Tax Scroll Summary | Rita | 2024-08-02
Electronic copy of tax scroll | Rita | 2024-08-02

## Steve
CITY OF CONCORD
WORKPAPERS FOR AUDIT
2024-06-30
Description of Item | Assigned To | Date Due | Completed
Purchase order cutoff | FYI only | 2024-05-17 | X
Send reminder to airport about 6/30 inventory count | Steve | 2024-06-21 | X
Regular monthly journal entries | All | 2024-07-10 | 2024-07-15
Run list of active CIP from Fixed Assets - email depts to ask for est completion date | Steve | 2024-07-12 | 2024-07-05
Last AP Check run for FY24 | FYI only | 2024-07-19 | FYI
Record accruals for purchased power | Steve | 2024-07-19 | 2024-07-12
Send reminder email to Engineering about developer donated asset info needed - need info by 8/2 | Steve | 2024-07-19 | 2024-07-11
Record all adjustments/corrections from physical asset verification | Steve | 2024-07-19 | 2024-07-15
Record all asset disposals | Steve | 2024-07-19 | 2024-07-15
Record all asset transfers | Steve | 2024-07-19 | 2024-07-15
Golf Course Bank Recon | Steve | 2024-07-19 | 2024-07-16
Airport CC recon | Steve | 2024-07-19 | 2024-07-11
Airport A/R aging recon | Steve | 2024-07-19 | 2024-07-11
Golf Course A/R recon | Steve | 2024-07-19 | 2024-07-16
Golf Course inventory listing | Steve | 2024-07-19 | 2024-07-11
Airport fuel inventory listing | Steve | 2024-07-19 | 2024-07-11
Golf course rainchecks listing | Steve | 2024-07-19 | 2024-07-11
Golf course gift certificates listing | Steve | 2024-07-19 | 2024-07-11
Request from Amanda spreadsheet for final cost allocations due 8/9 | Steve | 2024-07-19 | 2024-07-11
June P-Card transactions posting | FYI only | 2024-07-23 | FYI
Powell Bill asset information to Paige | Steve | 2024-07-24 | 2024-07-16
Recons for Airport deposit accounts | Steve | 2024-07-26 | 2024-07-11
Airport Fuel Revenue/Expense spreadsheets | Steve | 2024-07-26 | 2024-07-11
Purchase power spreadsheet | Steve | 2024-07-26 | 2024-07-25
Record all governmental vehicle & equipment additions | Steve | 2024-07-26 | 2024-07-26
Utilities revenue spreadsheet | Steve | 2024-07-26 | 2024-07-25
Water/Sewer & Electric Consumption Reports | Steve | 2024-07-26 | 2024-07-25
Top Water/Sewer/Electric Customers | Steve | 2024-07-26 | 2024-07-25
Reconcile Electric Sales tax spreadsheet to GL after cycle 2 posted | Steve | 2024-07-26 | 2024-07-25
Work with Electric to get info on projects recorded in operations to determine if any are capital | Steve | 2024-07-26 | 2024-07-25
Review housing 1001 assets to determine proper adjustments | Steve | 2024-07-26 | 2024-07-18
Record all enterprise fund vehicle & equipment additions | Steve | 2024-07-31 | 2024-07-31
Record all computer/software/building/land additions | Steve | 2024-07-31 | 2024-07-31
Record all other additions from 55 accounts not yet posted | Steve | 2024-07-31 | 2024-07-22
Record housing asset adjustments/cleanup | Steve | 2024-07-31 | 2024-07-18
Record electric operations project additions | Steve | 2024-07-31 | 2024-08-02
Record additions for all 58 accounts Compare with completion date provided by dept to ensure all captured. If dept says complete, there should be no open PO on project account. | Steve | 2024-07-31 | 2024-08-07
Record water/sewer contributed capital | Steve | 2024-08-01 | 2024-08-02
Record street contibuted capital (new JE) | Steve | 2024-08-01 | 2024-08-02
After all additions are entered in fixed asset module, review active CIP to see if any need to be put into service (based on est completion date or PO status) | Steve | 2024-08-01 | 2024-08-07
After all additions are entered, review capital outlay accts to ensure none are missing before posting depreciation | Steve | 2024-08-02 | 2024-08-02
Record any CIP put into service | Steve | 2024-08-02 | 2024-08-07
Record depreciation (save reports in Excel for auditors) | Steve | 2024-08-06 | 2024-08-13
Adjust contributed capital balances after depreciation is posted | Steve | 2024-08-07 | 2024-08-13
Allocation of internal service fund | Steve | 2024-08-08 | 2024-08-16
Reconciled fixed asset spreadsheet for each fund | Steve | 2024-08-09 | 2024-08-19
Copy of detail listing of additions, retirements and other adjustments for the year (Excel sheet for additions should include recon back to GL expense accounts for auditors) | Steve | 2024-08-09 | 2024-08-17
Provide a copy of the detail depreciation listing | Steve | 2024-08-09 | 2024-08-13
List of all contributed capital assets | Steve | 2024-08-09 | 2024-08-19
List of all infrastructure assets capitalized during the year and their related supporting documentation | Steve | 2024-08-09 | 2024-08-19
List of active CIP as of FY with estimated completion dates | Steve | 2024-08-09 | 2024-08-17
Audit trail (Excel) for all 4351000 accounts | Steve | 2024-08-09 | 2024-08-17
Fixed asset reports for ACFR (ensure all rollforwards balance to prev FY) | Steve | 2024-08-30 | 2024-08-26
Note on D8: Stephen: airport 6/21-6/30 posted 7/9 golf quarter 4 submitted 7/15 fleet allocation June - posted 7/11 Hillgrove Jun - posted 7/9
Note on D11: Stephen: CPP submitted 7/12 PEAK & NITSA submitted 7/11 and added to AP spreadsheet
Note on D35: Stephen: sent to Fred Porter on 7/25/24
Note on D38: Stephen: computers 7/31/24 bulidings 7/31/24 land to be included with project journal entry
Note on D39: Stephen: there is nothing to record for FY24
Note on D41: Stephen: updated backup on 8/2/24 (spreadsheet showed 6/30/22 updated 6/30/24)
Note on D42: Stephen: posted 8/2, then submitted corrections 8/7 after retainage entry was posted
Note on D43: Stephen: submitted 8/2
Note on D45: Stephen: submitted 8/7/24 due to retainage entry
Note on D47: Stephen: submitted 8/7/24 due to retainage entry
Note on D48: Stephen: posted 8/13 in GL morning, then depreciated FA system 8/13 afternoon
Note on D49: Stephen: submitted 8/13
Note on D50: Stephen: resubmitted 8/16/24
Note on D51: Stephen: general fund, first concord, enterprise fund spreadsheets reconciled 8/19/24
Note on D52: Stephen: submitted additions (with recon) and retirements to auditors on 8/17/24
Note on D54: Stephen: this is not a Suralink request but saved in Audit FY24, For Auditors, Workpapers, Steve, Fixed Assets, contributed capital folder
Note on D55: Stephen: 8/19 - printed FA listing for INFRASTRUCTURE, saved GASB entry, two other assets are from project entry
Note on D56: Stephen: submitted to auditors in Suralink 8/17/24
Note on D57: Stephen: submitted to auditors in Suralink 8/17/24
Note on D58: Stephen: 8/26 completed asset schedules